✦

# Complete Website Delivery Roadmap

Directions, dependencies, execution sessions, launch gates, and post-launch growth

Project document · Los Angeles · 25 June 2026

Prepared from the live-site audit and the current project canon.

# 1. Roadmap objective

Definition of success Deliver a launch-ready Los Angeles website that reliably attracts, qualifies, and records inquiries from families, private preschools, Montessori schools, and school programs — while preserving the locked Miss Lana brand, live-theater positioning, design system, and SEO architecture.

# 2. Workstreams

| ID | Direction | Scope |
| --- | --- | --- |
| A | Business decisions | Contacts, response process, logistics, travel, policies, documents, package rules |
| B | Content and conversion | Positioning, Home, CTA, forms, FAQs, pricing, proof, policies |
| C | Media | Photo selection, editing, video, gallery, social-ready clips |
| D | Pages and UX | Shell, Home, booking, school, birthday, shows, characters, about, gallery |
| E | Trust and B2B readiness | Reviews, bios, safety, school one-sheet, teacher resources, paperwork |
| F | SEO and migration | URLs, metadata, schema, GBP, Search Console, redirects, local visibility |
| G | Engineering and quality | Forms, analytics, performance, accessibility, testing, release |
| H | Growth after launch | Outreach, paid pilots, review engine, CRM, public-school strategy |

# 3. Dependency order

Confirm business facts and owner decisions.

Correct the current site and complete the conversion shell.

Make the inquiry pipeline work end to end.

Restructure Home and primary landing pages.

Prepare and install real media.

Add trust, policies, and B2B readiness.

Complete SEO, migration, analytics, and quality assurance.

Launch and then optimize from real inquiry data.

# 4. Session-by-session execution plan

## Session 01 — Decision lock and owner questionnaire

Direction: A   ·   Effort: Easy / fast

Choose one primary phone, booking email, SMS/WhatsApp policy, and preferred reply methods.

Confirm performer count, setup, space, power, outdoor rules, weather, parking, teardown, and photo time.

Confirm available documents: insurance, background checks, W-9, COI, invoice.

Decide deposit, cancellation, rescheduling, travel, and response-time rules.

Resolve show-name decisions and whether reviews are now officially in scope.

Session complete when: A signed-off decision sheet with no silent assumptions.

## Session 02 — Canon and backlog synchronization

Direction: A / B   ·   Effort: Easy / fast

Update core project truth where decisions changed, especially reviews.

Create a BLOCKER / HIGH / MEDIUM / LATER backlog.

Mark every page block as READY, ASSET, OWNER, TM, or TECH.

Freeze public facts and prohibited claims.

Session complete when: One authoritative backlog and no contradictions between documents.

## Session 03 — Current-site cleanup

Direction: B / D   ·   Effort: Easy / fast

Remove placeholders, preview labels, internal notes, and developer-facing copy.

Normalize 30+ years, LA location, ages, duration, starting price, and live-theater terminology.

Remove puppet-first, Russian, Slavic, “only/first/best,” and unsupported claims.

Unify button labels and phone presentation.

Session complete when: A credible public-facing work-in-progress site.

## Session 04 — Mobile conversion shell

Direction: D / G   ·   Effort: Easy–medium

Audit header, mobile menu, sticky Book CTA, click-to-call, and tap targets.

Ensure body text, contrast, focus states, keyboard access, and responsive spacing follow the design system.

Add persistent booking CTA and final CTA band to every public page.

Session complete when: A consistent conversion path on phone and desktop.

## Session 05 — Lead-form UX specification

Direction: B / G   ·   Effort: Medium

Finalize common fields and conditional school fields.

Add preferred contact method, indoor/outdoor, age range, ZIP, audience size, source attribution.

Write validation, error, success, privacy, and response microcopy.

Define spam protection and required/optional fields.

Session complete when: Approved form contract before implementation.

## Session 06 — Lead pipeline implementation

Direction: G   ·   Effort: Medium

Implement submission, owner notification, customer confirmation, and failure logging.

Store leads in Google Sheet or CRM with timestamp, source, service, and UTM.

Track successful inquiry, phone click, text click, and email click.

Test edge cases and delivery from mobile and desktop.

Session complete when: A reliable end-to-end inquiry system.

## Session 07 — Home information architecture

Direction: B / D   ·   Effort: Medium

Build Hero, Trust Strip, Format Explainer, service split, featured shows, school teaser, birthday teaser, video slot, reviews slot, team preview, How It Works, areas, and final form.

Remove repetitive sections and keep one primary message per viewport.

Confirm CTA hierarchy and price anchor.

Session complete when: A conversion-led Home page blueprint and approved copy hierarchy.

## Session 08 — Home production build

Direction: D / G   ·   Effort: Medium

Implement approved Home blocks using the locked design tokens.

Reserve media ratios to prevent layout shift.

Keep the LCP asset unanimated and ensure motion-safe behavior.

Complete responsive and accessibility review.

Session complete when: Production-ready Home page with temporary or final media.

## Session 09 — Media inventory and selection

Direction: C   ·   Effort: Medium

Collect all photos/videos and sort by Hero, Shows, Schools, Birthdays, Characters, Team, Reactions, Setup, Backstage.

Score for sharpness, emotional value, legal permission, composition, and brand fit.

Select launch minimums and identify missing shots.

Session complete when: A named, deduplicated launch-media library.

## Session 10 — Photo production

Direction: C   ·   Effort: Medium

Apply a consistent warm grade, natural skin, controlled saturation, crop standards, and export sizes.

Create hero, card, portrait, social, and OG variants.

Write alt text and confirm permissions.

Session complete when: Optimized, consistent images ready for implementation.

## Session 11 — Flagship video and short clips

Direction: C   ·   Effort: Medium–high

Edit a 45–75 second flagship reel showing scale, troupe, audience reaction, interaction, and finale.

Create captions, poster image, muted web version, and social vertical cuts.

Export performance-safe files.

Session complete when: One website proof video plus a reusable social clip set.

## Session 12 — School Shows content

Direction: B / E   ·   Effort: Medium

Define school promise, audience sizes, ages, SEL themes, setup, paperwork, consecutive performances, and quote logic.

Write school FAQ and B2B form copy.

Separate private preschool/Montessori offer from future public-school procurement.

Session complete when: Approved school landing-page content and offer.

## Session 13 — School Shows build

Direction: D / G   ·   Effort: Medium

Implement school hero, outcomes, what schools receive, logistics, trust, FAQ, and B2B form.

Add downloadable-resource slots without pretending unfinished documents exist.

Complete schema and metadata draft.

Session complete when: Launch-ready B2B landing page.

## Session 14 — Birthday offer definition

Direction: A / B   ·   Effort: Medium

Confirm birthday-child participation, greeting, photo moment, finale, add-ons, and restrictions.

Define the parent benefit: memorable experience without entertainment-management stress.

Write birthday FAQ and package copy.

Session complete when: A differentiated birthday product, not a renamed school show.

## Session 15 — Birthday page build

Direction: D / G   ·   Effort: Medium

Implement birthday hero, what is included, birthday-child moment, popular shows, price anchor, How It Works, FAQ, and form.

Use real family-event media and parent-oriented proof.

Session complete when: Launch-ready B2C landing page.

## Session 16 — Shows hub and content template

Direction: B / D   ·   Effort: Medium

Finalize show-card fields and detail-page content model.

Define best age, duration, moral, intensity/sensitivity note, interaction, venue fit, and related shows.

Lock clean English slugs and page metadata rules.

Session complete when: One reusable content/template contract for all eight shows.

## Sessions 17–20 — Eight show pages

Direction: B / D / C   ·   Effort: Medium

Build two show pages per session using the approved template.

Install final title, synopsis, values, age guidance, media, CTA, related shows, and schema.

Review each for duplicate copy and factual accuracy.

Session complete when: Eight complete, indexed show pages.

## Session 21 — Characters line

Direction: A / B / D   ·   Effort: Medium

Confirm available characters and actual format.

Write professional-troupe differentiation and duration/inclusion details.

Build the Characters page with real media and booking CTA.

Session complete when: A clear add-on/service line without generic mascot positioning.

## Session 22 — Pricing and service-area policy

Direction: A / B / D   ·   Effort: Medium

Finalize travel zones and package logic.

Build Birthday, Preschool, and School Assembly pricing sections.

Explain inclusions, quote triggers, larger groups, travel, and optional add-ons.

Avoid a complex calculator unless future data proves it useful.

Session complete when: Transparent pricing that qualifies rather than confuses leads.

## Session 23 — About, team, and professional proof

Direction: B / E / C   ·   Effort: Medium

Confirm the owner/director identity and all team roles.

Write 3–5 lines of concrete professional history per person.

Present Ukrainian theater heritage as a quiet background, not a slogan.

Build team proof, mission, values, and CTA.

Session complete when: A credible troupe page with named expertise.

## Session 24 — Reviews and proof system

Direction: E / G   ·   Effort: Medium

Collect, verify, permission, and structure at least five launch reviews.

Separate parent and educator proof.

Implement Home reviews, expanded proof section, and review-source links.

Create a post-event review request workflow.

Session complete when: A real social-proof layer and repeatable review engine.

## Session 25 — Gallery

Direction: C / D / G   ·   Effort: Medium

Build photo/video gallery with categories and accessible lightbox.

Lazy-load below-fold assets, reserve dimensions, and provide captions/alt text.

Keep illustrations subordinate to real performance media.

Session complete when: A fast, credible visual portfolio.

## Session 26 — FAQ, trust, and policies

Direction: A / B / E   ·   Effort: Medium

Publish confirmed logistics, safety, adult-supervision expectations, weather, cancellations, rescheduling, parking, and photo rules.

Create Privacy Policy, Terms, Cancellation/Rescheduling Policy, and required cookie disclosure.

Add professional-readiness information without unsupported claims.

Session complete when: Reduced buyer anxiety and launch-safe policies.

## Session 27 — SEO metadata and schema

Direction: F / G   ·   Effort: Medium–high

Write unique titles, descriptions, canonicals, Open Graph, and H1/H2 structure.

Implement LocalBusiness/PerformingGroup, Service, Breadcrumb, FAQ, and appropriate event/show schema.

Generate sitemap and robots rules; keep internal design pages noindex.

Session complete when: Search-engine-ready page set.

## Session 28 — Google Business Profile

Direction: F / E   ·   Effort: Medium

Find/claim or create the service-area profile.

Set accurate business name, categories, service areas, site, contacts, hours, services, photos, and videos.

Create a review acquisition process and GBP posting routine.

Session complete when: A complete local-search profile linked to the website.

## Session 29 — Domain migration and redirects

Direction: F / G   ·   Effort: Medium–high

Confirm control and renewal of both domains.

Map every old URL to the closest new URL with 301 redirects.

Set canonical host, HTTPS, Search Console properties, and sitemap submission.

Monitor 404s and redirect loops.

Session complete when: A clean move from the old domain without avoidable loss.

## Session 30 — Analytics and measurement

Direction: G / H   ·   Effort: Medium

Configure GA4, Search Console, GBP link tracking, and optional Meta Pixel.

Define conversions: inquiry success, call, text, email, show-to-booking path.

Create a simple lead/report dashboard and UTM naming rules.

Session complete when: Measurable acquisition and conversion data from day one.

## Session 31 — Performance and accessibility audit

Direction: G   ·   Effort: Medium–high

Audit Core Web Vitals, image delivery, font loading, video behavior, CLS, mobile performance, keyboard navigation, focus, contrast, labels, errors, and reduced motion.

Fix launch-blocking defects and verify on representative devices.

Session complete when: A fast, accessible site with no major technical blockers.

## Session 32 — Full pre-launch QA

Direction: G   ·   Effort: Medium

Test all routes, forms, devices, browsers, contact links, schema, metadata, 404, policies, redirects, analytics, and email delivery.

Perform content proofread and factual sign-off.

Create rollback and incident checklist.

Session complete when: A signed launch checklist with zero unresolved blockers.

## Session 33 — Production launch

Direction: F / G   ·   Effort: Medium

Deploy production, verify DNS/SSL/canonical behavior, submit sitemap, test live inquiries, inspect analytics and GBP links.

Monitor errors, 404s, form delivery, and performance during the launch window.

Session complete when: Stable public launch.

## Session 34 — First 30-day optimization

Direction: H   ·   Effort: Medium

Review queries, page paths, conversion, form abandonment, response time, lead quality, and service mix.

Improve weak copy/CTA/FAQ and prioritize the next content pages using evidence.

Do not create city pages until demand and query data justify them.

Session complete when: A measured optimization backlog.

## Session 35 — Growth channel launch

Direction: H   ·   Effort: Medium–high

Reactivate past clients, begin preschool/Montessori outreach, publish short video content, request reviews, and test high-intent Google Ads.

Track lead cost and booking quality by channel.

Pause broad low-intent campaigns that do not convert.

Session complete when: A controlled acquisition engine rather than random promotion.

## Sessions 36+ — Public-school track

Direction: E / H   ·   Effort: High

Research LAUSD and adjacent-district vendor/procurement requirements.

Prepare W-9, insurance, background checks, assembly pricing, learning objectives, teacher guide, technical rider, references, and outreach materials.

Pilot with PTAs, individual schools, or approved partners before scaling.

Session complete when: A separate school-sales system, not merely another website page.

# 5. Fast-win package

Recommended immediate sequence Sessions 01–06 are the fastest high-value package. They remove visible incompleteness, eliminate contradictory claims, improve mobile conversion, and make the inquiry pipeline operational before the full media and SEO build is finished.

Decision sheet and owner answers.

Canon/backlog synchronization.

Technical-copy cleanup.

Mobile CTA and navigation cleanup.

Form UX contract.

Working lead delivery and tracking.

# 6. Launch gates

| Gate | Requirement |
| --- | --- |
| Gate 1 — Business truth | Contacts, logistics, policies, travel, packages, and safety claims are confirmed. |
| Gate 2 — Conversion | Inquiry form, notifications, confirmation, logging, and tracking work reliably. |
| Gate 3 — Evidence | Real photos, flagship video, team proof, and minimum verified reviews are installed. |
| Gate 4 — Core pages | Home, School, Birthday, Shows, Pricing, About, Gallery, Booking, and policies are complete. |
| Gate 5 — Search and migration | GBP, metadata, schema, sitemap, Search Console, and 301 redirects are correct. |
| Gate 6 — Quality | Mobile, accessibility, performance, forms, links, analytics, and content pass QA. |
| Gate 7 — Operations | The owner can respond quickly, quote consistently, and track every lead. |

# 7. Activities explicitly deferred

Blog publishing before keyword and Search Console evidence.

Large-scale city landing-page production.

Online payment, customer accounts, or complex booking calendar.

Advanced quote calculator.

Full CRM automation before lead volume requires it.

Heavy character animation or large illustration production before trademark clearance.

Broad public-school expansion before paperwork and procurement readiness.

# 8. Final completion definition

Final standard The website is finished when it is not merely visually complete, but operationally able to attract a qualified visitor, prove trust, explain the exact service, collect a usable inquiry, notify the theater, measure the source, support follow-up, and remain discoverable and fast in local Los Angeles search.

# Project sources used

The document was prepared from: BRAND.md, PROJECT_BRIEF.md, 01_CONTENT_INVENTORY.md, 02_POSITIONING_AND_TONE.md, 03_SITEMAP_AND_SCOPE.md, 04_SEO.md, DESIGN_SYSTEM.md, SITE_STRUCTURE_AND_BLOCKS.md, the design-system research report, and the live-site audit of misslanatheater.com.

Canon rule: When this document conflicts with an updated core project file, the newest explicitly locked core file takes precedence.